## Sheet1
Attachment J – Risk Assessment – Provided to capture risk assessments undertaken across the City of Monash
Risk Assessment
Project Number: |  | N/a
Project Title: |  | Monash City Council Golf and Tennis Centre
Project Value: |  | Plus $20M
Created By: |  | Belinda Griffiths - Coordinator Recreation Services
Date Created: |  | 2020-09-01
When populating the Risk Assessment please refer to the Risk Management Reference Sheet (Appendix A) for further information in relation to Risk Ratings
Ref | Risk Description | Existing Controls in place | Consequence | Likelihood | Residual Risk Rating | Control Effectiveness Rating | Additional Controls to be put in place (For extreme or high risks) | Priority | Responsibility | Timeframe
| Given this project has only been conceptualised and hasn’t had detail design works completed. Cost escalations will be real and will become a risk of under producing/delivering the project scope because of limited money available. |  | 4 | C | High | effective | Council place an offering percentage to NELP and request all risks be shared as per the percentage breakdown | High | PCG | Throughout the project, importantly during detailed planning stage
| Contamination being found on site during construction | Complete a GeoTech report prior to works being completed | 3 | D | High | high effective | N/a | Medium | Project Manager | Once project announcement occurs
| Poor or no community consultation with the residents, community and clubs may resist change. | Continued community consultation must be had with all stakeholders, residents and the community | 4 | A | moderate | high effective | Complete a communications and consultation plan to ensure there is ongoing communication and consultation throughout the project | High | Project Manager, Council's Communications teams, Active Monash | Throughout the project
| Not appointing the Project Manager for the project early | Once the announcement is made on the successful Council. The Project Manager should be appointed straightway. | 5 | B | High | effective | Until the Project Manager is appointed, the Project should be driven by the Capital Works and Active Monash | High | Recreation Services | Once project announcement occurs
| Scope creep, throughout the detailed design and planning stage | Ensure there is effective planning done with all stakeholders throughout the project. | 2 | C | moderate | effective | N/a | Medium | Recreation Services | Throughout the project
| Aligning the contract management options for the project and the new company seeking changes to the design | Run this process early so that the contract manager of the centre has input into the project planning. | 2 | B | moderate | effective | Set the scene in the EOI or tender process | Medium | Recreation Services | Once project announcement occurs
| Consideration needs to be given to contract management, use of technologies and programs that haven’t been considered in the planning stage. I.e. different system to book-a-court | Run this process early so that the contract manager of the centre has input into the project planning. | 2 | B | moderate | high effective | Set the scene in the EOI or tender process | Medium | Recreation Services | Once project announcement occurs
| Scheduling risks and timeframe blow outs | Having an effective Project control group and PCG that is managing and overseeing the project | 4 | B | High | effective |  | Medium | Project Manager | Throughout the project
| Wet weather delaying the project for long unexpected times | Having an effective Project control group and PCG that is managing and overseeing the project | 3 | B | moderate | effective |  | Medium | Project Manager | Throughout the project
| Further lockdown and outbreaks of COVID-19 or a similar pandemic that stops or impacts the project |  | 3 | B | moderate | effective |  | Medium | Project Manager | Throughout the project
| Delays in supplier as a result of country lockdown or foreign affairs | early ordering of supplies and options to buy locally within Australia | 3 | B | moderate | effective |  | Medium | Project Manager | Throughout the project
| Reputational risks for Council and the State Government | Communication and consultation on this project needs to be first class | 4 | C | High | effective |  | Medium | Project Manager | Throughout the project
| Security to site risks and having to monitor the site more frequently than expected | Ensure the contractor has good security and Council also patrols the site throughout the project | 2 | B | moderate | effective |  | Medium | Project Manager | Throughout the project
| Appointed contracts going into administration or liquidation | ensure the contract makes consideration for this | 3 | A | moderate | effective |  | Medium | Project Manager | Throughout the project
| Residents not feeling heard or supported their voice has been heard on the project that they feel will impact them | Ensure effective communication, offer support to use the facilities and work with them about the assurance of screening and lighting spill will be managed. | 3 | C | moderate | effective | Install established trees, screening to help reduce, offer swim, golf and tennis memberships to the centre for 12 months. | High | Project Manager | Throughout the project
| Traffic management | Effectively manage the traffic flow in the site and around the precinct. Express the need for Jells and Waverley Road intersections to remain open throughout the project. | 4 | C | moderate | effective |  | Medium | Project Manager | Throughout the project
| Increased volume of traffic in the precinct due to new service. |  | 3 | C | moderate | effective |  | Medium | Council | Once the project has been completed